## Sheet1
Jeffrey's Worklog
Date | Summary | Hours | total so far:
2015-01-21 | First team meeting. Created meeting minutes folder. Added documents folder. Added all team members as colaborators to code repository. Added all team members to HipChat messaging system. Added minutes for jan21. Added Test folder. Moved all test documents to Test folder. | 2.5 | 98
2015-01-22 | Added assignment1. Created team leader information docx and availability spreadsheet. Added minutes from last meeting. Sent assignment1 to Scott Smoke for review. Added meeting folder. Tested automatic software documentation suite doc++. | 3
2015-01-27 | Printed team agenda. Wrote questions related to agenda. Team meeting. Walmart shopping for binders/organizational tools. Made template folder "MeetingTemplate". Researched time scheduling algorithms. Fixed mistakes made when attempting to synchronize both github and googledrive. | 3
2015-01-28 | Edited README.md to visually represent folder structure. Made a worklog template. | 1
2015-01-30 | Added questions document to be discussed at next team meeting. Team Meeting. Added minutes for meeting. Removed merged agenda and minutes. | 2
2015-02-01 | Updated READEME.md to reflect folder structure. Added first rought draft of client questions. Added first set of revised client questions. | 0.5
2015-02-02 | Team meeting. | 0.25
2015-02-05 | Housekeeping of tune_squad folder. Updated team agenda. Merged branch and squashed conflicts in repository. Added a trash can for all code | 0.75
2015-02-06 | Team meeting. | 0.5
2015-02-07 | Researched time table algorithms. | 2
2015-02-12 | Designed mockup with Josh Ford using Bolsomiq. Set up a meeting with the writing center to review Desktop Vs. Web app proposal. Added meeting minutes for 2-12-15. Created a client meeting folder. Updated README.md to reflect new folder structure. Researched best practices regarding how client/team meetings are conducted. Researched best practices for proposals. | 6
2015-02-13 | Team meeting. Discussed specification document requirements. Discussed questions. Edited team minutes for 2-13-2015 | 2.5
2015-02-14 | Researched specification document templates. | 1
2015-02-15 | Created specification document for group. Edited specification document. Made 4th set of client questions. | 2
2015-02-20 | Read IEEE specification document guidelines. Read the chapters named 'Requirements Trap' and 'Specification Trap' in the Pragmmatic Programmer book. Edited specifiction document. Added references and acknowledgements, Added user documentation, Defined intended audience, Added overview of document, Added Product Overview, Added application perspective, Added product functionality, Edited References, Added figure which describes format of generated schedules. Created use-case diagram for admin and general user. | 5
2015-02-23 | Added agenda. Added notes to spec doc. Added meeting folder for 2-22. Team meeting. | 2.5
2015-02-24 | Team meeting. Fixed merge conflicts. Updated spec doc. Client meeting. | 2.5
2015-02-25 | Updated minutes. Added client meeting minutes. Added Java language proposal. Read "Don't Make Me Think" front end designers guide. Updated folder structure. Put all client meeting questions in a single folder for team to access/reference them. | 3
2015-02-27 | Team meeting at 1:00pm. Worked on specification document. | 5
2015-02-28 | Worked on specification document. Read IEEE Std 830-1998 document. Formatted functional requirements based on user class (A3 template format). Updated section 3 to reflect that of IEEE Std 830-1998 standard. Updated font size and font type to be more consistent throughout document. Updated Table of Contents to reflect contents of document. Added multiple folders for submission versions of specdoc to client. | 2.5
2015-03-01 | Went through Java Scene Builder tutorial. Added standard format to input file. Cleaned document format. Reread specifications requirements chapter in text book for class. | 2
2015-03-02 | Updated specdoc 1.4. Added meeting agenda for next meeting. Added first ever draft of specdoc for references. | 1
2015-03-03 | Updated meeting minutes. Updated client questions/answers. Merge fix on git. | 2
2015-03-05 | Read coding standards worksheet. Added time constraint figure. Added draft of programming language proposal. Updated "answers to questions". Edited/updated specdoc. | 2
2015-03-06 | Team meeting. Updated specdoc sections 2.2 and 2.3. Uploaded Jordan's test files. Collaborated with Riley on coding standards. Updated definitions, acronym, abbreviations in specdoc. Added Screenshots for Version 1 and 2. Updated fonts. Updated references in document to match figures in appendix. | 5
2015-03-07 | Went through C# tutorial. Made first C# GUI project. Communicated with Jordan and uploaded his C++ program that generated test files. | 3
2015-03-09 | Read Mike Kruger's "C# Coding Style" document. Updated coding standards. Added coding standards to specdoc. | 3
2015-03-10 | Fixed TOC in specdoc. Printed specdoc. Team meeting. Helped josh setup visual studio 2013. Obtained product key from web. Aided in UML diagrams for each function of project as a different name space. Added the diagrams to LucidCharts. | 5
2015-03-12 | Cleaned up coding standards. Team meeting. | 2.5
2015-03-13 | Teacher meeting. | 2
2015-03-16 | Introduced LucidCharts to team. Distributed out username/pw to team. Created LIFES project folder. Added authentication namespace. Added a .gitignore file. | 2
2015-03-19 | Printed off final version of specdoc. Organized specodoc in binder, separated by tabs. Team meeting. Teacher meeting. Re-added Jordan as collaborator on github. | 3.5
2015-03-22 | Continued C# tutorial. Read "Pragmatic Programmer" | 2
2015-03-23 | Continued C# tutorial. | 1
2015-03-24 | Added play folder for Josh to have own space to practice C#. Worked with Scott on PDFsharp library that he found. Successfully created a PDF with library. | 1
2015-03-25 | Called everyone on the team to assure everyone knew the group was going to collaborate on project together. Worked with Riley and Scott on PdfSharp. Broke the code when pushing to git. Found the difference between "git revert" and "git reset". | 3
2015-03-27 | Researched transition screens for C#. Reviewed C# tutorial. | 2
2015-03-29 | Printed most documents in project. Put them into folders. Used HTML to display user manual. Failed attempt. Considering reverting to LaTeX. | 5
2015-03-30 | Worked with Scott to fix project on github. Correctly reverted changes to repository. Team meeting. | 2
2015-03-31 | Team meeting. | 1.5